## TASKS
PROJECT PLAN
MY TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Project Alignment | 2020-01-17 | 2020-01-17 | 100% | 1 | Basic Project Description, Slack Channel and GitHub. Meeting with Marcos.
Business Requirements SOW (work in progress) Submit doc on the website | 2020-01-24 | 2020-01-24 | 0% | 0 | Develop a rational statement based on a business problem statement. Define the process in key metrics to benchmark output from proposed solution and verify they will provide business/technical value. Refine the problem statement to ensure alignment with the identified proposed solution. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
SOW (final version) Submit doc on the website | 2020-02-07 | 2020-02-07 | 0% | 0 | Identify the data requirements and related data sources to assist in solving the problem statement. Create a set of data assumptions, limitations, and constraints required to move forward with the data. Define the methodology and testing procedures required to develop the problem framework and action plan.Final version of all documents with all updates discussed with Marcos during the interactions via slack or in-person. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Data Aqusition Acquisition and Understanding Submit doc on the website | 2020-02-07 | 2020-02-07 | 0% | 0 | Perform exploratory data analysis to identify main characteristics within the data. Determine preliminary data manipulations requirements (i.e. harmonize, rescale and/or clean) to increase the validity in the dataset. Perform statistical analysis to identify data patterns and correlations. Discuss the benefits of feature engineering for optimal model output. Identify key candidate features between synthesized and real data for model input. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Modelling (part 1) Submit doc on the website | 2020-02-14 | 2020-02-14 | 0% | 0 | Evaluate model(s) structures explored in program to help solve the problem statement. Assess and select appropriate software tools to successfully work with the data and model(s). Select calibration model techniques and processes to increase accuracy and viability within output. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Modelling (part 2) Submit doc on the website | 2020-02-21 | 2020-02-21 | 0% | 0 | Discuss model(s) architecture and software pipeline needed to successfully create the proposed solution. Assess dataset assumptions, limitations, and constraints in order to develop effective models. Identify the selection criteria for model creation and evaluation Create a model selection scorecard (i.e. evaluation and validation). Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Project - Quality Assurance Submit doc on the website | 2020-02-28 | 2020-02-28 | 0% | 0 | Create an Evaluation Report to record and communicate key findings. Work with results from scorecard to analyze pros and cons. Communicate scorecard results formally within report as an evaluation report. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Prototyping Submit doc on the website | 2020-03-06 | 2020-03-06 | 0% | 0 | Prototype the proposed model architecture using the selected software. Begin feeding data into model architecture and observe output. Begin necessary model tweaking in order to ensure desired results. Evaluate model and consider alternatives if necessary. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Delopyment Warmup (part 1) | 2020-03-07 | 2020-03-26 | 0% | 0 | Identify the business validation procedures for model structure and metrics. Determine data manipulations requirements (i.e. harmonize, rescale and/or clean) to increase the validity in the models. Create model validation procedures to ensure model accuracy and validity. Begin building model saving, loading, and re-training procedures if necessary, for new ingress data. Update GitHub. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Delopyment Warmup (part 2) | 2020-03-07 | 2020-03-26 | 0% | 0 | Run finalized model structures and metrics for Final Term Report. Determine data manipulations requirements (i.e. harmonize, rescale and/or clean) to increase the accuracy and validity in the models. Review feedback from Preliminary report. Update GitHub. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Delopyment Warmup (part 3) Submit doc on the website | 2020-03-07 | 2020-03-27 | 0% | 0 | Development of software pipeline to host proposed model solution. Development of solution end-point to be consumed via service by the final user (Data Scientist) Meet with professor to gauge progress and guide accordingly. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Pre-Deployment | 2020-03-28 | 2020-04-16 | 0% | 0 | Evaluate the business benefit of the model over time (i.e. 3 or 5 year timeline) Develop findings and final recommendations. Finalize slide deck to accompany Final Report. Update GitHub. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Deployment | 2020-03-28 | 2020-04-16 | 0% | 0 | All solution components should be ready to work in production. Update GitHub. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.
Production and Final Presentation Submit doc on the website | 2020-04-17 | 2020-04-17 | 0% | 0 | Finalize formal report for submission and Technology demo. Update GitHub. Submit doc on the website. Keep your Product Manager (Marcos) 100% aligned with your project outcomes.